## Progress Resistance Metric
Instructions:
1. Enter all tasks that are scheduled to start or be in progress during the current reporting period.
2. Enter the planned start date, remaining duration in workdays, and actual progress this period for each task.
3. Enter the project name at top right and the report date (the closing date of the reporting period).
4. The total progress resistance metric is calculated at bottom-right. In the example it's 63%.
5. This means that no progress was made in 63% of available working time in the reporting period.
6. Conversely, progress was made in 37% of available working time in the reporting period.
7. This suggests there are opportunities to investigate why the project was idle slighly less than two-thirds of the time.
Progress Resistance Metric
[5 empty] | Project: | XG600
Report Date (R): | [5 empty] | 2023-11-17
| A | B | C | D | E | F
Task | Planned Start | Remaining Duration in Workdays\ (Beginning) | Actual Progress This Period | Workdays from Planned Start to Report Date (R - A) | Maximum Workdays Through Report Date (Min B, D) | Progress Resistance Metric 1 - (C / E)
1 | 2023-11-06 | 10 | 5 | 10 | 10 | 50%
2 | 2023-11-06 | 12 | 0 | 10 | 10 | 100%
3 | 2023-11-06 | 3 | 2 | 10 | 3 | 33.33%
4 | 2023-11-07 | 8 | 3 | 9 | 8 | 62.5%
5 | 2023-11-07 | 2 | 0 | 9 | 2 | 100%
6 | 2023-11-08 | 10 | 2 | 8 | 8 | 75%
7 | 2023-11-09 | 10 | 5 | 7 | 7 | 28.57%
8 | 2023-11-10 | 1 | 1 | 6 | 1 | 0%
|  | Totals: | 18 |  | 49 | 63.27%
Formulas:
D = IF([A]>H15, "N/A - Start Date in Future", IF(NETWORKDAYS([A],H15) > 0, NETWORKDAYS([A],H15), 0))